## Sheet1
Top 10 | Risk Type | Risk Description | Occurrence Probability | Impact | Qualitative Analysis | Potential Indicators | Strategy
1 | People | Poor Team coordination and team work within the team | Low | High | 3 | Frequent occurance of miscommunication Poor staff morale Poor relationships between team members | (Avoidance) Update individual work prgress in weekly meetings to ensure everyone is on track for their work deadlines Team outings to help bond team members
2 | Technology | Software development bugs | High | Medium | 6 | QA Team detect bugs in the Software | (Mitigation) QA Team conduct regular review of the software and investigate and corrected them as soon as possible
3 | Organisational | Unrealistic expectations by the senior management | High | High | 9 | Mangement rushing the project deadline, increasing number of functional requirement etc | (Mitigation) Conduct meetings with Senior management regularly to let them know the progress and correct their estimation
4 | Technology | The database system is unable to process as many transactions per second as expected | Low | Low | 1 | Performance assessment report on database system indicates that the throughput is below the required amount | (Contigency) Assess the need to purchase a higher performance database
5 | Requirements | Change in Functional Requirement and require major refactor of the software | Medium | High | 6 | Functions in the software are tightly coupled | (Mitigation) Derive traceability information to assess requirements change impact (Avoidance) Use software methods that are not tightly coupled to other parts of the software
6 | Estimation | The size of the Software is underestimated | Medium | Medium | 4 | Deadlines are not met Unpredictable software complexities | (Mitigation) Schedule buffers for each task to prevent delays in project schedule (Avoidance) Use past historical data from past project to have a better estimation of project scehdules
7 | Estimation | Unable to meet the agreed deadline to submit the deliverables | Medium | Medium | 4 | Developers asking for extension for software development Progress of Development Team are slow | (Avoidance) Team Project Manager conduct Weekly meetings with Developer Team to check progress and change deadline if needed
8 | People | Team member not experienced in using tech stack for our project | Medium | Medium | 4 | App development progress is slow | (Mitigation) Seek technical consultants for help
9 | People | Key team members are ill or are unable to attend critical meetings | Low | Medium | 2 | Staff health deteriorating Poor staff morale | (Avoidance) Practice good hygiene practices (Mitigation) Reorganize the team such that there is more overlap of work to allow people to understand each other's jobs
10 | Organisational | Organisational Financial Problems | Low | Medium | 2 | Staff wages delayed Software licensing not paid | (Mitigation) Re-evalulate technology and non-technology related cost and change if needed