## Instructions
Activities During the Planning Meet:
| Estimated Task Priority: | Each team member select a value between 0 (most unimportant) to 10 (most important) from the drop down list based on his/her own understanding about the task.
| Estimated Task Difficulty: | Each team member select a value between 0 (extremely easy) to 10 (extremely difficult) from the drop down list based on his/her own understanding about the task.
| Estimated Task Time Required: | Each team member select a value between 1 to 14 days from the drop down list based on his/her own understanding about the task.
| Confidence about the Task: | Each team member select a value between 0 (not confident at all) to 10 (extremely confident) from the drop down list based on his/her own understanding about the task and his/her own capabilities.
| Assignee's Mood: | Excited | Happy | Neutral | Sad | Depressed
| Task Assignee: | Team members should discuss among themselves to distribute the tasks. If there are tasks which remain unassigned after the discussion, team lead will decide to whom the remaining task(s) should be delegated.
Activities During the Subsequent Planning Meeting
Review for each task: if it has been completed (Yes/No), rate the quality of the result (0: Extremely Bad -10: Excellent)

## Lab 1
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Das Atrik | Kelvin Chua | Melvin Chua | Padhi Abhinandan | Rajuravi Vishal Raj | Goh Hong Xiang, Bryan
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited | Excited
1. Project Proposal |  | Task Quality Evaluation (After Task Completed) | 9 | 8 | 9 | 9 | 9 | 9 | 8.5 | 7.1667 | 11.3333 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan | Through Discussion | Yes | 12 | Excited | 8.8333
| Estimated Task Priority（0-10） |  | 10 | 10 | 6 | 10 | 6 | 9
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 7 | 6 | 7 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 11 | 12 | 13 | 7 | 13 | 12
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 9 | 9 | 9 | 6
2. Use Case |  | Task Quality Evaluation (After Task Completed) | 9 | 9 | 8 | 9 | 8 | 8 | 8.1667 | 6 | 10.5 | Melvin Chua | Kelvin Chua | Through Discussion | Yes | 5 | Excited | 8.5
| Estimated Task Priority（0-10） |  | 8 | 8 | 9 | 9 | 9 | 6
| Estimated Task Difficulty（0-10） |  | 8 | 6 | 5 | 5 | 5 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 9 | 10 | 12 | 10 | 12 | 10
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 8 | 9 | 8 | 5
3. Meeting Minutes 1 |  | Task Quality Evaluation (After Task Completed) | 6 | 10 | 9 | 7 | 9 | 8 | 3.4 | 7.3333 | 6.3333 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan Melvin Chua Kelvin Chua | Through Discussion | Yes | 3 | Excited | 8.1667
| Estimated Task Priority（0-10） |  | 4 | 2 | 4 | 3 | 4 | 4
| Estimated Task Difficulty（0-10） |  | 7 | 5 | 9 | 8 | 9 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 13 | 8 | 1 | 8 | 7
| Team Member's Confidence about the Task (0-10) |  | 5 | 7 | 6 | 5 | 6 | 9
4. Meeting Minutes 2 |  | Task Quality Evaluation (After Task Completed) | 9 | 9 | 8 | 8 | 8 | 8 | 5.3333 | 7.1667 | 7.8333 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan Melvin Chua Kelvin Chua | Through Discussion | Yes | 3 | Excited | 8.3333
| Estimated Task Priority（0-10） |  | 9 | 2 | 6 | 4 | 6 | 5
| Estimated Task Difficulty（0-10） |  | 8 | 7 | 6 | 7 | 8 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 12 | 13 | 1 | 13 | 7
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 5 | 7 | 5 | 9
5. Media Wiki |  | Task Quality Evaluation (After Task Completed) | 10 | 9 | 9 | 9 | 9 | 8 | 6.1667 | 3.5 | 2.1667 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan Melvin Chua Kelvin Chua | Through Discussion | Yes | 2 | Excited | 9
| Estimated Task Priority（0-10） |  | 7 | 6 | 5 | 8 | 5 | 6
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 4 | 4 | 3 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 3 | 1 | 2 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 7 | 9 | 7 | 7

## Lab2
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Das Atrik | Kelvin Chua | Melvin Chua | Padhi Abhinandan | Rajuravi Vishal Raj | Goh Hong Xiang, Bryan
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited | Excited
1. SRS |  | Task Quality Evaluation (After Task Completed) | 9 | 9 | 10 | 10 | 8 | 8 | 9.1667 | 7.5 | 10 | Das Atrik | Goh Hong Xiang, Bryan Padhi Abhinandan | Through Discussion | Yes | 12 | Excited | 9
| Estimated Task Priority（0-10） |  | 8 | 9 | 9 | 10 | 9 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 7 | 8 | 8 | 7 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 11 | 9 | 10 | 12 | 8 | 10
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 8 | 9 | 9 | 8
2. Quality Management Plan |  | Task Quality Evaluation (After Task Completed) | 9 | 9 | 10 | 10 | 9 | 9 | 8.1667 | 6.5 | 12.1667 | Melvin Chua | Kelvin Chua, Vishal | Through Discussion | Yes | 12 | Excited | 9.3333
| Estimated Task Priority（0-10） |  | 8 | 9 | 8 | 8 | 8 | 8
| Estimated Task Difficulty（0-10） |  | 6 | 7 | 5 | 6 | 8 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 12 | 12 | 11 | 13 | 12 | 13
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 10 | 9 | 10 | 9
3. Meeting Minutes 3 |  | Task Quality Evaluation (After Task Completed) | 8 | 10 | 10 | 10 | 10 | 7 | 5.3333 | 2.5 | 1 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan Melvin Chua Kelvin Chua | Through Discussion | Yes | 1 | Excited | 9.1667
| Estimated Task Priority（0-10） |  | 6 | 6 | 4 | 5 | 6 | 5
| Estimated Task Difficulty（0-10） |  | 3 | 2 | 4 | 2 | 2 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 7 | 9 | 8 | 9 | 8 | 8
4. Media Wiki |  | Task Quality Evaluation (After Task Completed) | 10 | 9 | 9 | 9 | 9 | 8 | 6.1667 | 3.5 | 2.1667 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan Melvin Chua Kelvin Chua | Through Discussion | Yes | 2 | Excited | 9
| Estimated Task Priority（0-10） |  | 7 | 6 | 5 | 8 | 5 | 6
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 4 | 4 | 3 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 3 | 1 | 2 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 7 | 9 | 7 | 7

## Lab3
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Das Atrik | Kelvin Chua | Melvin Chua | Padhi Abhinandan | Rajuravi Vishal Raj | Goh Hong Xiang, Bryan
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited | Excited
1. Project Plan |  | Task Quality Evaluation (After Task Completed) | 9 | 8 | 7 | 10 | 8 | 8 | 8.3333 | 7.3333 | 13 | Das Atrik | Goh Hong Xiang, Bryan Padhi Abhinandan | Through Discussion | Yes | 19 | Excited | 8.3333
| Estimated Task Priority（0-10） |  | 8 | 9 | 8 | 9 | 9 | 7
| Estimated Task Difficulty（0-10） |  | 7 | 7 | 10 | 7 | 7 | 6
| Estimated Time Required for the Task（1-21 Days） |  | 19 | 8 | 2 | 18 | 14 | 17
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 9 | 9 | 9 | 8
2. Risk Management Plan |  | Task Quality Evaluation (After Task Completed) | 9 | 8 | 7 | 8 | 9 | 9 | 7.8333 | 5.6667 | 6.3333 | Melvin Chua | Kelvin Chua, Vishal | Through Discussion | Yes | 10 | Excited | 8.3333
| Estimated Task Priority（0-10） |  | 8 | 9 | 9 | 8 | 8 | 5
| Estimated Task Difficulty（0-10） |  | 3 | 7 | 5 | 6 | 8 | 5
| Estimated Time Required for the Task（1-21 Days） |  | 10 | 2 | 2 | 9 | 8 | 7
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 10 | 9 | 10 | 9
3. Meeting Minutes 4 |  | Task Quality Evaluation (After Task Completed) | 8 | 10 | 8 | 10 | 10 | 7 | 5.3333 | 2.5 | 2 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan Melvin Chua Kelvin Chua | Through Discussion | Yes | 1 | Excited | 8.8333
| Estimated Task Priority（0-10） |  | 6 | 6 | 4 | 5 | 6 | 5
| Estimated Task Difficulty（0-10） |  | 3 | 2 | 4 | 2 | 2 | 2
| Estimated Time Required for the Task（1-21 Days） |  | 2 | 2 | 2 | 2 | 2 | 2
| Team Member's Confidence about the Task (0-10) |  | 7 | 9 | 8 | 9 | 8 | 8
4. Media Wiki |  | Task Quality Evaluation (After Task Completed) | 10 | 9 | 9 | 9 | 9 | 8 | 6.6667 | 3.5 | 2 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan Melvin Chua Kelvin Chua | Through Discussion | Yes | 2 | Excited | 9
| Estimated Task Priority（0-10） |  | 7 | 6 | 8 | 8 | 5 | 6
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 4 | 4 | 3 | 3
| Estimated Time Required for the Task（1-21 Days） |  | 2 | 2 | 2 | 2 | 2 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 7 | 9 | 7 | 7
5. Coding the app |  | Task Quality Evaluation (After Task Completed) | 7 | 9 | 10 | 9 | 9 | 8 | 9.6667 | 9.5 | 19.3333 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan Melvin Chua Kelvin Chua | Through Discussion | Yes | 21 | Excited | 8.6667
| Estimated Task Priority（0-10） |  | 10 | 9 | 9 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 10 | 9 | 10 | 10 | 9 | 9
| Estimated Time Required for the Task（1-21 Days） |  | 21 | 18 | 14 | 21 | 21 | 21
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 9 | 9 | 7 | 5

## Lab4
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Das Atrik | Kelvin Chua | Melvin Chua | Padhi Abhinandan | Rajuravi Vishal Raj | Goh Hong Xiang, Bryan
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited | Excited
1. Design Report on Software Maintainability |  | Task Quality Evaluation (After Task Completed) | 9 | 8 | 7 | 10 | 8 | 6 | 7.6667 | 6.8333 | 7 | Das Atrik | Goh Hong Xiang, Bryan Padhi Abhinandan | Through Discussion | Yes | 7 | Excited | 8
| Estimated Task Priority（0-10） |  | 8 | 7 | 8 | 8 | 9 | 6
| Estimated Task Difficulty（0-10） |  | 6 | 7 | 10 | 7 | 7 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 10 | 2 | 10 | 8 | 5
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 9 | 9 | 9 | 7
2. Release Plan |  | Task Quality Evaluation (After Task Completed) | 9 | 8 | 7 | 8 | 9 | 7 | 7.1667 | 5.3333 | 6.5 | Melvin Chua | Kelvin Chua, Vishal | Through Discussion | Yes | 6 | Excited | 8
| Estimated Task Priority（0-10） |  | 8 | 8 | 9 | 8 | 4 | 6
| Estimated Task Difficulty（0-10） |  | 5 | 4 | 5 | 6 | 8 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 6 | 9 | 2 | 7 | 8 | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 10 | 9 | 10 | 9
3. Software Configuration Management Plan |  | Task Quality Evaluation (After Task Completed) | 8 | 9 | 8 | 10 | 10 | 7 | 6 | 3.5 | 3.8333 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan Melvin Chua Kelvin Chua | Through Discussion | Yes | 7 | Excited | 8.6667
| Estimated Task Priority（0-10） |  | 7 | 7 | 4 | 7 | 6 | 5
| Estimated Task Difficulty（0-10） |  | 4 | 2 | 4 | 7 | 2 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 2 | 2 | 8 | 2 | 4
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 8 | 8 | 8 | 8
4. Change Management Plan |  | Task Quality Evaluation (After Task Completed) | 10 | 9 | 9 | 9 | 9 | 8 | 6.6667 | 4.5 | 3.3333 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan Melvin Chua Kelvin Chua | Through Discussion | Yes | 7 | Excited | 9
| Estimated Task Priority（0-10） |  | 7 | 6 | 8 | 8 | 5 | 6
| Estimated Task Difficulty（0-10） |  | 7 | 3 | 4 | 7 | 3 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 6 | 2 | 2 | 6 | 2 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 7 | 8 | 7 | 7
5. Meeting Minutes 5 |  | Task Quality Evaluation (After Task Completed) | 7 | 8 | 10 | 9 | 9 | 8 | 5.5 | 7 | 3.1667 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan Melvin Chua Kelvin Chua | Through Discussion | Yes | 1 | Excited | 8.5
| Estimated Task Priority（0-10） |  | 3 | 9 | 9 | 2 | 5 | 5
| Estimated Task Difficulty（0-10） |  | 4 | 9 | 10 | 1 | 9 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 5 | 2 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 9 | 10 | 7 | 5
6. Coding the app |  | Task Quality Evaluation (After Task Completed) | 10 | 8 | 7 | 10 | 9 | 9 | 9.1667 | 10 | 14 | Melvin Chua | Kelvin Chua, Vishal | Through Discussion | Yes | 14 | Excited | 8.8333
| Estimated Task Priority（0-10） |  | 10 | 9 | 9 | 10 | 10 | 7
| Estimated Task Difficulty（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Time Required for the Task（1-14 Days） |  | 14 | 14 | 14 | 14 | 14 | 14
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 10 | 10 | 10 | 5
7. Media Wiki |  | Task Quality Evaluation (After Task Completed) | 9 | 8 | 7 | 8 | 9 | 9 | 7.6667 | 4.3333 | 1.5 | Melvin Chua | Kelvin Chua, Vishal | Through Discussion | Yes | 1 | Excited | 8.3333
| Estimated Task Priority（0-10） |  | 8 | 9 | 9 | 7 | 8 | 5
| Estimated Task Difficulty（0-10） |  | 1 | 3 | 5 | 4 | 8 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 2 | 2 | 2 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 10 | 9 | 5 | 9

## Lab5
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Das Atrik | Kelvin Chua | Melvin Chua | Padhi Abhinandan | Rajuravi Vishal Raj | Goh Hong Xiang, Bryan
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited | Excited
1. CMMI level 2 definition |  | Task Quality Evaluation (After Task Completed) | 9 | 8 | 7 | 7 | 8 | 6 | 7.6667 | 6.8333 | 6 | Das Atrik | Goh Hong Xiang, Bryan Padhi Abhinandan | Through Discussion | Yes | 7 | Excited | 7.5
| Estimated Task Priority（0-10） |  | 8 | 7 | 8 | 8 | 9 | 6
| Estimated Task Difficulty（0-10） |  | 6 | 7 | 10 | 7 | 7 | 4
| Estimated Time Required for the Task（1-7 Days） |  | 4 | 10 | 2 | 7 | 8 | 5
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 9 | 7 | 9 | 7
2. Test Cases and Requirements Test Coverage Report |  | Task Quality Evaluation (After Task Completed) | 9 | 8 | 7 | 8 | 9 | 7 | 7.1667 | 5.3333 | 5.6667 | Melvin Chua | Kelvin Chua, Vishal | Through Discussion | Yes | 6 | Excited | 8
| Estimated Task Priority（0-10） |  | 8 | 8 | 9 | 8 | 4 | 6
| Estimated Task Difficulty（0-10） |  | 5 | 4 | 5 | 6 | 8 | 4
| Estimated Time Required for the Task（1-7 Days） |  | 3 | 9 | 2 | 5 | 8 | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 10 | 9 | 10 | 9
3. Test Plan |  | Task Quality Evaluation (After Task Completed) | 8 | 9 | 8 | 9 | 10 | 7 | 6.1667 | 3.5 | 3.5 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan Melvin Chua Kelvin Chua | Through Discussion | Yes | 7 | Excited | 8.5
| Estimated Task Priority（0-10） |  | 7 | 7 | 4 | 8 | 6 | 5
| Estimated Task Difficulty（0-10） |  | 4 | 2 | 4 | 7 | 2 | 2
| Estimated Time Required for the Task（1-7 Days） |  | 5 | 2 | 2 | 6 | 2 | 4
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 8 | 8 | 8 | 8
4. Presentation Slides |  | Task Quality Evaluation (After Task Completed) | 10 | 9 | 9 | 9 | 9 | 8 | 7 | 8 | 5.1667 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan Melvin Chua Kelvin Chua | Through Discussion | Yes | 7 | Excited | 9
| Estimated Task Priority（0-10） |  | 7 | 6 | 8 | 10 | 5 | 6
| Estimated Task Difficulty（0-10） |  | 7 | 6 | 8 | 10 | 8 | 9
| Estimated Time Required for the Task（1-7 Days） |  | 6 | 5 | 4 | 6 | 7 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 7 | 9 | 7 | 7
5. Meeting Minutes 6 |  | Task Quality Evaluation (After Task Completed) | 7 | 8 | 10 | 9 | 9 | 8 | 2 | 2 | 1.5 | Das Atrik | Goh Hong Xiang, Bryan Rajuravi Vishal Raj Padhi Abhinandan Melvin Chua Kelvin Chua | Through Discussion | Yes | 1 | Excited | 8.5
| Estimated Task Priority（0-10） |  | 3 | 2 | 1 | 3 | 1 | 2
| Estimated Task Difficulty（0-10） |  | 1 | 2 | 3 | 1 | 2 | 3
| Estimated Time Required for the Task（1-7 Days） |  | 1 | 2 | 1 | 2 | 2 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 9 | 10 | 7 | 5
6. Media Wiki |  | Task Quality Evaluation (After Task Completed) | 9 | 8 | 7 | 8 | 9 | 9 | 7.6667 | 1.6667 | 1.5 | Melvin Chua | Kelvin Chua, Vishal | Through Discussion | Yes | 1 | Excited | 8.3333
| Estimated Task Priority（0-10） |  | 8 | 9 | 9 | 7 | 8 | 5
| Estimated Task Difficulty（0-10） |  | 1 | 2 | 1 | 3 | 2 | 1
| Estimated Time Required for the Task（1-7 Days） |  | 1 | 1 | 2 | 2 | 2 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 10 | 9 | 5 | 9